## Sheet1
| Project Management |  | Data Pipleine |  |  | Modelling | Results | Modelling | Results |  | Dashboard Development |  |  |  |  | Writing
Date - w/c | Define the Scope and Title | Literature Review | Data Collection | Data Processing | Data Validation | Model Development - ML Methods | Model Testing - ML Methods | Model Development - DL Methods | Model Testing - DL Methods | Backtesting Development | Plan | Develop UI | Set up APIs | Adding Models | Hosting | Proposal | Presentation | Report | Proof Reading
2025-11-03 | ✅ | ✅
2025-11-10 | ✅ | ✅
2025-11-17 | ✅ | ✅
2025-11-24 | ✅ | ✅ | Start creating script ✅ | [7 empty] | ✅
2025-12-01 |  |  | Finish creating script
2025-12-08 |  |  | Run script to collect data
2025-12-15 |  |  | Run script to collect data | Clean OHLCV | [11 empty] | Introduction
2025-12-22 |  |  |  | Clean Macro
2025-12-29 |  |  |  | Clean GT
2026-01-05 |  |  |  | Clean NYT | Validate OHLVC
2026-01-12 |  |  |  | Clean NYT | Validate Macro | [10 empty] | Literature Review
2026-01-19 |  |  |  |  | Validate GT
2026-01-26 |  |  |  |  | Validate NYT
2026-02-02 |  |  |  |  | Validate NYT
2026-02-09 | [5 empty] | Develop Models - Linear Reg + SVM | [9 empty] | Project Management
2026-02-16 | [5 empty] | Develop Models - RF - XGBoost
2026-02-23 | [5 empty] | Develop Models - MLP
2026-03-02
2026-03-09 | [6 empty] | Evaluate all models on the | [8 empty] | Conclusion |  | Introduction
2026-03-16 | [6 empty] | test sets
2026-03-23 | [7 empty] | Develop - LSTM
2026-03-30 | [7 empty] | Develop - Hybrid Model
2026-04-06 | [17 empty] | Literature Review
2026-04-13 | [15 empty] | Proof Read
2026-04-20 | [8 empty] | Evaluate all models on the | [7 empty] | Intro + Background
2026-04-27 | [8 empty] | test sets
2026-05-04 | [16 empty] | Aimss + Objectives | Methodology
2026-05-11 | [9 empty] | Develop backtesting
2026-05-18 | [16 empty] | Dataset
2026-05-25
2026-06-01 | [16 empty] | Methods + Results | Results
2026-06-08
2026-06-15 | [16 empty] | Discussion
2026-06-22
2026-06-29 | [16 empty] | Proof Read | Discussion
2026-07-06 | [16 empty] | Record
2026-07-13
2026-07-20
2026-07-27 | [17 empty] | Abstracts
2026-08-03
2026-08-10
2026-08-17
2026-08-24
2026-08-31
Report
Key Deadlines | Date | Status
Data Ready | 9th Feb | In Progress
Introduction Complete | 6th April | In Progress
Models Developed | 12th April | Not - Started
Models Validated | 27th April | Not - Started
Literature Review Complete | 10th May | In Progress
Results Collected | 1st June | Not - Started
Methods Draft Complete | 1th June | Not - Started
Results Draft Complete | 29th June | Not - Started
Dashboard Complete | 19th July | In Progress
First Draft Finished | 2nd August | Not - Started
Final Draft Complete | 24th August | Not - Started